## Project plan
Project name: | Facodi.pt – Faculdade Comunitária Digital: Collaborative Documentation & Inclusive Software Platform
Project leader(s): | Marcelo Santos (University of Algarve)
Project activity
| March, 2026 | April, 2026 | May, 2026 | June, 2026 | July, 2026 | August, 2026 | September, 2026 | October, 2026 | November, 2026
Activity 1: Setup & Design | X | X
Activity 2: Prototype & Content Integration |  |  | X | X | X
Activity 3: Multilingual Collaboration & Refinement | [5 empty] | X | X
Activity 4: Testing, Dissemination & Evaluation | [7 empty] | X | X
Remark: Highlight with color/fill the field if the activity is scheduled during that time.